## Lesson Learnt_24
| Observations | Solution | ETA
Start the SAP applications at DR site | VMs have host files. Basis didnt update hostfiles with the correct IP address. It had the current (production server ip address) | Create DR hostfile "host.dr" | 2024-09-30
|  | Update DR SOP - Ping test to included for correct IP addresses | 2024-09-30
Manually invoked DNS | CMS to check config files on PPO, PWM, PRP, RTR |  | 2024-10-04

## PRD HANA
Sl No | Phases | Steps | Owner | Planned Start Date | Planned End Date | Duration | Downtime | Date | Start Time (SAST) | End Time (SAST) | Status | Comments |  | Actual Start Time (SAST) - FY'25 | Actual End Time (SAST) - FY'25 |  | Actual Start Time (SAST) - FY'24 | Actual End Time (SAST) - FY'24 |  | Actual Start Time (SAST) - FY'23 | Actual End Time (SAST) - FY'23
DR Testing Plan for HANA PROD Systems (PBI/PH4, PRP/PH1, PWM/PH2)
Planning
1 | ASR health check |  | CMS |  |  |  |  | 2025-05-18
2 | HANA Replication (ASYNC + LOGREPLAY) from Primary to DR | Check the connectivity status | Basis AMS |  |  |  |  | 2025-05-18 |  |  |  | No action required
3 | ASR for the SAP application servers. | Check the connectivity status | CMS |  |  |  |  | 2025-05-21 | 13:00 | 14:00 |  | CMS team will check and confirm | [7 empty] | 13:00 | 14:00
4 | Root access to be given to Basis team for all QA and Production VM | isapqrp00,isapqwm00, isapqbi00, ihdbqh100, ihdbqh200, ihdbqh400, isapprp00, isapprp01, isappwm00, isappwm01, isappwm02, isappbi00, ihdph100, ihdbph200, ihdbph400 | CMS |  |  |  |  | 2025-05-21 | 14:00 | 15:30 |  | SR request on 20th May . SR to be raised . | [7 empty] | 14:00 | 15:30
5 | Request for Firefighter ID in PRP, PWM and PBI |  | Basis AMS/ DP World |  |  |  |  | 2025-05-21 |  |  |  | Firefighter ID valid date - 22nd, 23rd, 24th
DR Testing Phase
1 | Lock all Business users Except testing User | PRP, PWM, PGW | New Era |  |  |  |  | 2025-05-24 | 5:00 | 5:30 |  | Rashid to share the POC | New Era |  |  |  | 5:00 | 5:08 |  | 5:00 | 5:30
2 | Stop Background jobs if required | PRP, PWM, PBI | Basis AMS |  |  |  |  | 2025-05-24 | 5:30 | 6:00 | [6 empty] | 5:08 | 5:11 |  | 5:30
3 | Stop SAP PO | Stop SAP PO Server | Basis AMS | [13 empty] | 5:02 | 5:10
4 | Stop Web dispatcher | Stop Web dispatcher Server | Basis AMS | [13 empty] | 5:02 | 5:08
5 | Stop all replication on PLT | Stop PLT replication | Basis AMS | [8 empty] | Rashid to confirm |  |  |  |  | 5:02 | 5:10
6 | Unmount sftp in fstab in PRP | isapprp00, isapprp01 | CMS | [13 empty] | 5:11 | 5:17 | Unmount SFTP took longer then expected |  | 7:00
7 | Execute pre DR test functional report | BOBJ/BODS need to be stopped after pre-function testing | New Era |  |  |  |  | 2025-05-24 | 6:00 | 7:30 |  | Rashid to share the POC | New Era |  |  |  | 5:17 | 6:43 |  | 7:00 | 8:50
8 | Stop SAP Application and DB on Primary | Shutdown VMs PH1, PH2, PH4 | Basis AMS |  |  |  |  | 2025-05-24 | 7:30 | 8:30 | [6 empty] | 6:43 | 6:58 |  | 8:50
9 | Stop the Quality System (Application + DB) | [15 empty] | 6:43 | 7:15
10 | Provide HANA DB Server DNS change list to Infra | Rename hostname QH1, QH2, QH4 | Basis AMS | [13 empty] | 6:58 | 7:33
11 | Perform takeover to DR HANA database |  | Basis AMS |  |  |  |  | 2025-05-24 | 8:30 | 10:30 |  | change the DR hostname with assigining a hostname as primary and execute a HANA hostname change. |  |  |  |  | 7:33 | 9:14 |  |  | 09;38
12 | Spin the application VM on DR site by ASR |  | CMS |  |  |  |  | 2025-05-24 |  |  |  | Servers handed over by CMS to Basis for Valdidation at 8:43 Validations completed by Basis at 9:55 |  |  |  |  | 7:33 | 8:43 |  | 9:39 | 10:14
13 | Update DNS |  | Wayne Kapp |  |  |  |  | 2025-05-24 | 10:30 | 12:00 |  | Seeking help from Wayne on mentioned servers DNS did not update (isapppo00 , isapprp00 , isapprp01, isappwm00, isaprtr00) |  |  |  |  | 8:56 | 9:35 |  | 10:21
| Once vnet peering is broken connect to EU west VPN to access resources | Remove VNET PEERING between West and other Regions | Wayne Kapp | [13 empty] | 9:40 | 10:30
|  | Allow only DOMAIN SERVICES for servers in SAP – to all AD servers | Hylton/Shaun | [13 empty] | 9:40 | 10:00
|  | Confirm VPN access to West Region | DP World | [7 empty] | Information(No action required) | Hylton to confirm VPN details |  |  |  |  | - | -
|  | Install required repository and packages required for joining the domain. | DP World
|  | Configure /etc/hosts/ and /etc/resolv.conf config file to have all relevant DNS entries. | [9 empty] | Check on this as ASR showed not required
Ensure all ports associated with running all domain joining commands are open.
|  | Join the machine to domain using REALM command. | [9 empty] | May not be necessary as the ASR testing showed it is not required
|  | Enter Server IP entries for DNS lookups (Both Forwarding and Reverse) | [18 empty] | 11:54
14 | Rename host file QH1, QH2 & QH4 in DR site | Rename hosts to hosts_primary (As already have a file called hosts_DR) rename hosts_DR to hosts Ping to test if all systems are working with correct IPs in DR | CMS |  |  |  |  | 2025-05-24 | 12:00 | 12:30 |  | isapprp00,isapprp01,isappwm00,isappwm01,isappwm02,isappbi00,isapppo01,isapppo00,isappgr00,isap pgw00, isappb100,isappds00,isapplt00.
15 | Reconfigure the connections from SAP to HANA at DR site. | There should be no entry in /etc/hosts for all servers | Basis AMS |  |  |  |  | 2025-05-24 | 12:00 | 12:30 |  | This step is not required to be performed |  |  |  | (Basis took lunch break of 17min) | 10:47 | 11:04 |  | 11:55
16 | Rename host files in ASR application servers | Rename hosts to hosts_primary (As already have a file called hosts_DR) rename hosts_DR to hosts | CMS |  |  |  |  | 2025-05-24 | 12:30 | 13:30 |  | isapprp00,isapprp01,isappwm00,isappwm01,isappwm02,isappbi00,isapppo01,isapppo00,isappgr00,isap pgw00, isappb100,isappds00,isapplt00.
17 | Start the SAP applications at DR site | Start the SAP applications at DR site | Basis AMS |  |  |  |  | 2025-05-24 | 12:30 | 13:30 |  | Issue on PPO and PRP01 , working on the same PRP01 up at 16:12 PPO up at 16:57 |  |  |  | Issues observed on systems ¦¦ Incorrect IP was updated on PH200 | 11:04 | 16:57
18 | Check and apply PO license, if needed | Basis to update the license required | [14 empty] | 15:23 | 16:57
19 | Disable batch jobs, Scot etc. Need to check with Imperial | Check to be done to verify | Basis AMS |  |  |  |  | 2025-05-24 | 13:30 | 14:30 |  | Only testing is in scope in DR. Any changes done in DR will not be replicated to Primary | Only check to be done
20 | Sanity check of the systems |  | Basis AMS/CMS
21 | Handover the system for testing |  | Basis AMS/Imperial | [8 empty] | PRP00 handed over for testing at 15:23 |  |  |  |  | 15:23 | 16:57 |  |  | 14:46
20 | Execute post DR test functional report |  | DP World |  |  |  |  | 2025-05-24 | 14:30 | 16:00 |  | Rashid to communicate to functional via Whatsapp channel | New Era |  |  |  | 15:23 | 16:15 |  | 14:46
21 | Compare reports between environments and give feedback |  | DP World | [17 empty] | 15:21
Failback DR
1 | Stop the application and DB on DR site |  | Basis AMS |  |  |  |  | 2025-05-24 | 16:00 | 17:30 |  | Everything other than PPO move to stop state : Start time: 16:21 |  |  |  |  | 16:21 | 17:03 |  | 15:22
2 | Stop the ASR VMs |  | CMS | [13 empty] | 16:26 | 17:07 |  |  | 16:15
3 |  | Add VNET PEERING between West and other regions | Wayne Kapp |  |  |  |  | 2025-05-24 | 17:30 | 18:30 | [6 empty] | 17:36 | 17:47
|  | Enable all firewall policies to allow access to West Region | DP World
|  | Fall back for server computer object to be picked up is to run “realm leave” command and re-join domain again for new object to be picked. | DP World
4 | Decommision the Application VMs (Created by ASR) |  | CMS |  |  |  |  | 2025-05-24 | 18:30 | 19:30 | [6 empty] | 17:07 | 17:26 |  |  | 18:13
5 | Revert the hostname as previous (QA) via HANA hostname change (QH1,QH2,QH4) |  | CMS |  |  |  |  | 2025-05-24 | 19:30 | 20:00 | [6 empty] | 17:13 | 17:30
6 | Rename host file QH1, QH2 & QH4 in DR site | Rename hosts to hosts_DR (As already have a file called hosts_DR) rename hosts_primary to hosts | CMS |  |  |  |  | 2025-05-24
7 | Rename DB(PH1,PH2, PH4) back to DR DB name (QH1, QH2 and QH4) | Rename DBs | Basis |  |  |  |  | 2025-05-24 | 20:00 | 21:00 | [6 empty] | 17:22 | 17:52
8 | Start the HANA DB and Application in Primary site |  | Basis/CMS | [13 empty] | 18:07 | 20:51
9 | Change the DNS Back | Bring up all Production VMs in primary location( SA North and Europe North) | CMS/DP World | [8 empty] | DNS to be updated manually for PWM00,PRP01 still pointing to DR IP PGW facing issue in bringing up, Rest all were up at 19:07 PGW up at 20:47 after restore |  |  |  |  | 17:54 | 20:47
10 | Basic health check of the system |  | Basis AMS |  |  |  |  | 2025-05-24 | 21:00 | 21:30 | [6 empty] | 19:30 | 20:55
11 | Handover the system to Imperial |  | Basis AMS/DP World
12 | Execute reports on production after failback |  | DP World |  |  |  |  | 2025-05-24 | 21:30 | 23:00 |  | Started testing at 19h26 but could not finish because of PGW . Started PGW testing at 20:56 Rashid to communicate to functional via Whatsapp channel |  |  |  |  | 19:26 | 21:10
13 | Compare reports between environments and give feedback |  | DP World | [17 empty] | 19:51
14 | Register the Secondary DR DB |  | Basis AMS | [8 empty] | Revert the hostname as previous (QA) via HANA hostname change |  |  |  |  | 21:05 | 21:26 |  | 19:51 | 20:35
15 | Bring up the Quality APP+DB |  | Basis | [13 empty] | 21:34 | 21:55 |  | 19:51 | 20:35
16 | Mount sftp in fstab in PRP | isapprp00, isapprp01 | CMS |  |  |  |  | 2025-05-24 | 23:00 | 23:30 | [6 empty] | 21:02 | 21:28 |  | 20:36 | 20:43
17 | Unlock all users |  | DP World | [8 empty] | Rashid to communicate to functional via Whatsapp channel | New Era |  |  |  | 21:10 | 21:28 |  | 20:44 | 20:59
18 | Start Bactch Jobs |  | Basis |  |  |  |  | 2025-05-24 | 23:30 | 0:00 | [6 empty] | 21:29 | 21:34 |  | 21:00
19 | Start PO & Web Dispatcher & Gateway |  | Basis AMS | [13 empty] | 21:12 | 21:25
20 | Start PLT Replication | Start PLT Replication | Basis AMS | [13 empty] | 21:34 | 21:36 |  |  | 21:25
21 | DR test complete | [16 empty] | 21:55 |  | 21:30 | 21:30

## PRD SQL
Sl No | Phases | Steps | Owner | Duration | Downtime | Status | Comments
DR Testing Plan for SQL PROD Systems (PB1 and PDS)
Planning
1 | Setup SQL Replication to DR |  | SQL DB Team |  |  |  | No action required
2 | ASR setup for the SAP application servers. |  | CMS Team |  |  |  | CMS team will check and confirm
DR Testing Phase
1 | Stop the Application(Tomcat and CIA) on BOBJ(isappb100) |  | Basis AMS
2 | Stop the Application (Tomcat and CIA) on BODS(isappds00) |  | Basis AMS
3 | Stop the DB on PDS(isappds00) |  | SQL DB Team
4 | Spin the BOBJ application VM on DR site by ASR |  | CMS Team
5 | Spin the BODS application and DB VM on DR site by ASR |  | CMS Team
6 | Update DNS |  | CMS/Imperial
|  | Disable VNET PEERING between West and other Regions | Imperial
|  | Allow only DOMAIN SERVICES for servers in SAP – to all AD servers | Imperial
|  | Confirm VPN access to West Region | Imperial
Install required repository and packages required for joining the domain.
Configure /etc/hosts/ and /etc/resolv.conf config file to have all relevant DNS entries.
Ensure all ports associated with running all domain joining commands are open.
Join the machine to domain using REALM command.
Enter Server IP entries for DNS lookups (Both Forwarding and Reverse)
7 | Restore the databases on ASR VM server with the DB backup taken from isappds00 | Not required | SQL DB Team |  |  |  | Not required
8 | Fix the orphan users | Not required | SQL DB Team |  |  |  | Not required
9 | Vadidate SQL DB Status |  | SQL DB Team
10 | Start the application on BODS(isappds00) |  | Basis AMS
11 | Start the application on BOBJ(isappb100) |  | Basis AMS
12 | Handover the system for testing |  | BasisAO/Imperial
Failback DR
1 | Stop the applications: BOBJ and BODS |  | Basis AMS
2 | Stop the DB SQL() |  | SQL DB Team
3 | Stop the VMs |  | CMS
4 | Change the DNS Back |  | CMS/Imperial
|  | Enable VNET PEERING between West and other regions | Imperial
|  | Enable all firewall policies to allow access to West Region | Imperial
Fall back for server computer object to be picked up is to run “realm leave” command and re-join domain again for new object to be picked.
5 | Drop the restored databases. | not required | SQL DB Team |  |  |  | not required
6 | Decommision the Application VMs (Created by ASR) |  | CMS
7 | Start the DB on PDS(isappds00) |  | SQL DB Team
8 | Start the application on BODS(isappds00) on Primary site |  | Basis AMS
9 | Start the application on BOBJ(isappb100) on Primary site |  | Basis AMS
10 | Basic health check of the system |  | Basis AMS
11 | Handover the system to Imperial |  | Basis AMS/Imperial

## PRD Sybase
Sl No | Phases | Steps | Owner | Planned Start Date | Planned End Date | Duration | Downtime | Start Time (SAST) | End Time (SAST) | Status | Comments
DR Testing Plan for Sybase PROD Systems (PGW, PGR, PPO, PLT)
Planning
1 | Setup Sybase Replication (ASYNC) from Primary to DR |  | Basis AMS | [7 empty] | No action required
2 | ASR setup for the SAP (application+DB) servers |  | CMS | [7 empty] | CMS team will check and confirm
3 | Root access to be given to Basis team for all Production VM | isapppo01, isapppo00, isappgr00, isappgw00, isapplt00 | CMS |  |  |  |  | 2023-09-15
DR Testing Phase
4 | Lock all Business users |  | Imperial | [7 empty] | Rashid to share the POC
5 | Stop Background jobs if required |  | Basis AMS
6 | Stop SAP Application and DB on Primary |  | Basis AMS
7 | Stop the Primary VM |  | CMS
8 | Spin the New ASR VM in Secondary Region |  | CMS
9 | Transfer the backup and logs from Azure to new ASR VM |  | Basis AMS/CMS | [7 empty] | Not required in Dr test
10 | Initiate DB restore | Restore the latest backup | Basis AMS | [7 empty] | Not required in Dr test
Apply the logs
11 | Update DNS |  | CMS/Imperial | [7 empty] | NSG part need to discussed with Rashid
|  | Disable VNET PEERING between West and other Regions | Imperial
|  | Allow only DOMAIN SERVICES for servers in SAP – to all AD servers | Imperial
|  | Confirm VPN access to West Region | Imperial
|  | Install required repository and packages required for joining the domain. | Imperial
|  | Configure /etc/hosts/ and /etc/resolv.conf config file to have all relevant DNS entries. | Imperial
|  | Ensure all ports associated with running all domain joining commands are open. | Imperial
|  | Join the machine to domain using REALM command. | Imperial
|  | Enter Server IP entries for DNS lookups (Both Forwarding and Reverse) | Imperial
12 | Start the SAP application. |  | Basis AMS
13 | Disable batch jobs, Scot etc. Need to check with Imperial |  | Basis AMS | [7 empty] | Only testing is in scope in DR. Any changes done in DR will not be replicated to Primary
14 | Sanity check of the systems |  | BasisAO/CMS
15 | Handover the system for testing |  | BasisAO/Imperial
Failback DR
1 | Stop the application and DB in secondary site |  | Basis AMS
2 | Stop the VMs in secondary site |  | CMS
3 | Change the DNS Back |  | CMS/Imperial
|  | Enable VNET PEERING between West and other regions | Imperial
|  | Enable all firewall policies to allow access to West Region | Imperial
|  | Fall back for server computer object to be picked up is to run “realm leave” command and re-join domain again for new object to be picked. | Imperial
4 | Start the Sybase DB and Application on Primary |  | Basis AMS
5 | Basic health check of the system |  | Basis AMS
6 | Start Batch Jobs |  | Basis AMS
7 | Handover the system to Imperial |  | Basis AMS/Imperial

## Functional Test
Functional Test Pre / During / Post
1 | Stock balances in ERP and EWM – Division HF (AstraZeneca)
2 | Stock balances in ERP and Flonet – Division LO (Sanulac)
3 | Debtors Book /Open Line Items – Division HF (AstraZeneca)
4 | General Ledger Balance –Depreciation Account
5 | Open Sales Orders – Division HF (AstraZeneca)
6 | Last Invoice number Processed
7 | Number of Customers and Vendors – SE16 table extract
8 | Number of Materials/Products – SE16 table extract
9 | EWM Idoc count Pre and Post
10 | ERP Idoc count Pre and Post
11 | EWM Queue count Pre and Post
12 | BW Reports
Hi Rashid,
Please refer to the table below for the SAP MM, PM & SD Tables that require validation during the SAP DR Testing on Sunday, 19th September 2021.
These Tables are Transactional & could have the propensity to change during the DR Testing, ergo it is imperative that they are evaluated.
This requirement was also highlighted as a requirement by the Accenture Basis Team during the Meeting.
The Master Data Tables remain Static over weekends, so are not relevant for DR Testing.
Hi Saleha,
Please include the SAP FI/CO bits & bobs required for the DR Testing.
Thanx,
Mel
Hi Mel
Thank you for the below.
I have added the tables for FI.
The rest of my testing is open item reports and trial balances.
Regards
Saleha
Table | Table Text | Package | Package Description | Module
AUFK | Order master data | KAUF | Cost Accounting, Orders | PM
EBAN | Purchase Requisition | ME | Purchasing | MM
EKBE | History per Purchasing Document | ME | Purchasing | MM
EKKN | Account Assignment in Purchasing Document | ME | Purchasing | MM
EKKO | Purchasing Document Header | ME | Purchasing | MM
IFLOTX | Functional Location: Short Texts | ILOM | Application Development R/3 Location Management | PM
LIKP | SD Document: Delivery Header Data | VL | WS-SHP: General Processing for Shipping | SD & MM
LIPS | SD document: Delivery: Item data | VL | WS-SHP: General Processing for Shipping | SD & MM
MKPF | Header: Material Document | MB | Application development R/3 inventory management | MM
MSEG | Document Segment: Material | MB | Application development R/3 inventory management | MM
QMEL | Quality Notification | IWOC | Application Development R/3 Work Order Cycle | PM
VBAK | Sales Document: Header Data | VA | Application development R/3 Sales | SD
VBAP | Sales Document: Item Data | VA | Application development R/3 Sales | SD
VBRK | Billing Document: Header Data | VF | Application development R/3 invoice | SD
VBRP | Billing Document: Item Data | VF | Application development R/3 invoice | SD
BSEG | Accounting Document Segment | FBAS | Financial Accounting | FI
BKPF | Accounting Document Header | FBAS | Financial Accounting | FI

## system info
SAP System | Type | SID | DB | Hostname | ASR Enabled | Region
PO | Application | PPO | N/A | isapppo01 | Yes | South Africa North
| DB | PPO | Sybase | isapppo00 | Yes | South Africa North
EWM | Application | PWM | N/A | isappwm00 | Yes | South Africa North
| Application | PWM | N/A | isappwm01 | Yes | South Africa North
| Application | PWM | N/A | isappwm02 | Yes | South Africa North
| DB | PH2 | HANA | ihdbph200 |  | South Africa North
| DR | PH2 | HANA | ihdbqh200 |  | Europe West
ECC | Application | PRP | N/A | isapprp00 | Yes | South Africa North
| Application | PRP | N/A | isapprp01 | Yes | South Africa North
| DB | PH1 | HANA | ihdbph100 |  | South Africa North
| DR | PH1 | HANA | ihdbqh100 |  | Europe West
BW/BI | Application | PBI | N/A | isappbi00 | Yes | Europe North
| DB | PH4 | HANA | ihdbph400 |  | Europe North
| DR | PH4 | HANA | ihdbqh400 |  | Europe West
GRC | Application + DB | PGR | Sybase | isappgr00 | Yes | Europe North
Gateway/Fiori | Application + DB | PGW | Sybase | isappgw00 | Yes | Europe North
SLT | Application + DB | PLT | Sybase | isapplt00 | Yes | Europe North
Web Dispatcher | Application | PWD | N/A | isappwd00 | Yes | Europe North
BOBJ | Application | PB1 | SQL | isappb100 | Yes | Europe North
DS | Application + DB | PDS | SQL | isappds00 | Yes | Europe North
Solman | Application | SMA | N/A | isappsa00 | Yes | Europe North
| DB | PH6 | HANA | ihdbhsa00 |  | Europe North
| DR | PH6 | HANA | ihdbhsa00dr |  | Europe West
Print Server | Application | NA | N/A | isapprt00 | Yes | South Africa North
Telnet | Application | NA | N/A | isapptn00 | Yes | South Africa North
Telnet | Application | NA | N/A | isapptn01 | Yes | South Africa North

## ASR Info
VM\Host Name | IP Address in Primary region | IP Address (Static) in ASR Region | OS | ASR Enabled (Y\N) | Region | Environment | Status | Failover | Failback and cleanup | Deviation, if any | Remarks
isappb100 | 172.31.29.10 | 172.31.34.47 | Windows | Y | North Europe | Production | Healthy
isappbi00 | 172.31.29.5 | 172.31.34.52 | Linux | Y | North Europe | Production | Healthy
isappds00 | 172.31.29.70 | 172.31.34.53 | Windows | Y | North Europe | Production | Healthy
isappgr00 | 172.31.29.6 | 172.31.34.51 | Linux | Y | North Europe | Production | Healthy
isappgw00 | 172.31.29.7 | 172.31.34.50 | Linux | Y | North Europe | Production | Healthy
isapplt00 | 172.31.29.8 | 172.31.34.49 | Linux | Y | North Europe | Production | Healthy
isapppo00 | 172.31.37.8 | 172.31.34.46 | Linux | Y | South Africa North | Production | Healthy
isapppo01 | 172.31.37.7 | 172.31.34.58 | Linux | Y | South Africa North | Production | Healthy
isapprp00 | 172.31.37.4 | 172.31.34.62 | Linux | Y | South Africa North | Production | Healthy
isapprp01 | 172.31.37.5 | 172.31.34.57 | Linux | Y | South Africa North | Production | Healthy
isapprt00 | 172.31.36.68 | 172.31.34.48 | Windows | Y | South Africa North | Production | Healthy
isapptn00 | 172.31.36.69 | 172.31.32.61 | Windows | Y | South Africa North | Production | Healthy |  |  |  |  | 172.31.32.61
isapptn01 | 172.31.36.70 | 172.31.32.4 | Windows | Y | South Africa North | Production | Healthy |  |  |  |  | 172.31.32.4
isappwd00(Primary) | 172.31.29.12 | 172.31.34.55 | Linux | Y | North Europe | Production | Healthy
isappwd00(Secondary) | 172.31.29.14 | 172.31.34.54 | Linux | Y | North Europe | Production | Healthy
isappwm00 | 172.31.37.9 | 172.31.34.56 | Linux | Y | South Africa North | Production | Healthy
isappwm01 | 172.31.37.10 | 172.31.34.61 | Linux | Y | South Africa North | Production | Healthy
isappwm02 | 172.31.37.11 | 172.31.34.59 | Linux | Y | South Africa North | Production | Healthy
isaprtr00 | 172.31.28.4 | 172.31.32.62 | Linux | Y | North Europe | Production | Healthy
isapprp02 | 172.31.37.6 | 172.31.34.60 | Linux | Y | South Africa North | Production

## HANA DR DNS Changes
Before DR
172.31.37.68 ihdbph100.imperial.local ihdbph100
172.31.37.69 ihdbph200.imperial.local ihdbph200
172.31.29.69 ihdbph400.imperial.local ihdbph400
172.31.34.201 ihdbqh100.imperial.local ihdbqh100
172.31.34.204 ihdbqh200.imperial.local ihdbqh200
172.31.34.203 ihdbqh400.imperial.local ihdbqh400
During DR
#172.31.37.68 ihdbph100.imperial.local ihdbph100 (hash out Production HANA IP)
#172.31.37.69 ihdbph200.imperial.local ihdbph200 (hash out Production HANA IP)
#172.31.29.69 ihdbph400.imperial.local ihdbph400 (hash out Production HANA IP)
172.31.34.201 ihdbqh100.imperial.local ihdbqh100 ihdbph100.imperial.local ihdbph100 (Add Production DB host alias to Quality DB IP)
172.31.34.204 ihdbqh200.imperial.local ihdbqh200 ihdbph200.imperial.local ihdbph200 (Add Production DB host alias to Quality DB IP)
172.31.34.203 ihdbqh400.imperial.local ihdbqh400 ihdbph400.imperial.local ihdbph400 (Add Production DB host alias to Quality DB IP)
DR Failback
172.31.37.68 ihdbph100.imperial.local ihdbph100 (Revert back earlier settings)
172.31.37.69 ihdbph200.imperial.local ihdbph200 (Revert back earlier settings)
172.31.29.69 ihdbph400.imperial.local ihdbph400 (Revert back earlier settings)
172.31.34.201 ihdbqh100.imperial.local ihdbqh100 (Revert back earlier settings)
172.31.34.204 ihdbqh200.imperial.local ihdbqh200 (Revert back earlier settings)
172.31.34.203 ihdbqh400.imperial.local ihdbqh400 (Revert back earlier settings)

## Team Info
Team | Resource | Email Id | SAP Access | Contact Number
SDM | Supriya Gupta | supriya.x.gupta@accenture.com |  | 91 9818820213
ACN Basis | Siddharth Sahay | siddharth.a.sahay@accenture.com | Yes | 91 9538625658
ACN Basis | Satyabrat Sethi | satyabrat.sethi@accenture.com | Yes | 91 9337605771
ACN Basis | Ayush kumar Sahu | ayush.kumar.sahu@accenture.com | Yes | 91 8989510824
ACN Basis | Medha Nainala | medha.nainala@accenture.com | Yes | 91 9494717700
ACN CMS | Priyanka Balachandran | p.c.balachandran@accenture.com |  | 91 9164782112
ACN CMS | Rajeev Maulekhi | rajeev.maulekhi@accenture.com |  | 91 9999787953
ACN CMS | Vivek Joshi | vivek.e.joshi@accenture.com |  | 91 8057758446
ACN CMS | Manish Garg | manish.i.garg@accenture.com |  | 91 9999181589
ACN CMS | Chilaka Haswitha | chilaka.haswitha@accenture.com |  | 91 9550065657
ACN SM | Anshuma Tandon | anshuma.tandon@accenture.com |  | 91 7838652950
ACN SM | Pralekha Mohantay | pralekha.mohanty@accenture.com |  | 91 9776176949
ACN DBA | Siraj shaik | siraj.a.shaik@accenture.com |  | 91 8885114770
ACN DBA | Sudheer Kumar | sudheer.kumar.alla@accenture.com |  | 91 9347033170
Network | Shaun Constable
Server | Isaac Modisane
Azure | Wayne Kapp
Basis | Rashid Mahomed |  |  | +27 82 490 0037
SAP Functional
SAP Functional
SAP Functional | Gerhard Goosen
SAP Functional
SAP Functional
SAP Functional

## VM_Backup
Not Required

## DB_Backup
Not Needed
HANA DB backup configuration in Azure
1. Key Creation
a. Create BAKUPADMIN key in HDBuserstore for taking backups.
Execute the following command for creating the key:
hdbuserstore SET BACKUPADMIN ihdbh100.imperial.local:30215 SYSTEM
b. Check on the successful creation of the key.
To check on the success of the creation of the key, execute the command: hdbuserstore LIST
2. Downloading and executing the configuration Script
a. Go to the Microsoft Azure portal => Recovery Services vaults
Select the service vault that is there in the same location as your VM
b. Go to Backup Items=> SAP HANA in Azure VM
c. Click the Add button.
d. Click on Start Discovery
e. Download the configuration Script.
Scroll to the bottom of the page and download the configuration script by clicking on highlighted this.
Copy the azure script to database server.
f. Run the script:
./msawb-plugin-config-com-sap-hana.sh -s DH1 -n 02 --system-key BACKUPADMIN
3. Configure Backup
a. Log into the Azure Portal=> Recovery Service Vault
Select the service vault that is there in the same location as your DB VM
b. Select Backup Items => SAP HANA in Azure VM.
Click on the Add button
c. Select on the Configure Backup and select your DB form the options.
d. Check the progress in view details.
4. Set up Backup Policy
5. Assign the backup policy to the VM and the DB
6. Initiate the first Full Backup
a. Initiate the first full backup from the Azure Portal by selecting the Backup item from the Recovery service vault and then clicking on the Backup Now option.
b. Check on the backup progress from the Backup Jobs.
Sybase Backups
For the Sybase systems we have the below crontab scripts configured which are responsible to run the backup.
# * * * * * *
# ¦ ¦ ¦ ¦ ¦ ¦
# ¦ ¦ ¦ ¦ ¦ +-- Year (range: 1900-3000)
# ¦ ¦ ¦ ¦ +---- Day of the Week (range: 1-7, 1 standing for Monday)
# ¦ ¦ ¦ +------ Month of the Year (range: 1-12)
# ¦ ¦ +-------- Day of the Month (range: 1-31)
# ¦ +---------- Hour (range: 0-23)
# +------------ Minute (range: 0-59)
#--------------------------------------------------------------------------
*/15 * * * * /sybase/PGR/scripts/Sybase_Backups_LOG.sh PGR LOG 2>&1 #Sybase logbackup every 5 mins
00 18 * * * /sybase/PGR/scripts/Sybase_Backups_FULL_D.sh PGR FULL 2>&1 #Sybase full backup Daily
00 21 1 * * /sybase/PGR/scripts/Sybase_Backups_FULL_M.sh PGR FULL 2>&1 #Sybase full backup on 1st of every month
30 23 1 7 * /sybase/PGR/scripts/Sybase_Backups_FULL_Y.sh PGR FULL 2>&1 #Sybase full backup on 1st of every July
##
#02 13 * * * /sybase/PGR/scripts/Sybase_Backups_FULL_D.sh PGR FULL 2>&1 #Adhoc
#29 11 * * * /sybase/PGR/scripts/Sybase_Backups_LOG.sh PGR LOG 2>&1 #Adhoc
SQL DB backup configuration in Azure
1. Configure Backup
a. Log into the Azure Portal=> Recovery Service Vault
Select the service vault that is there in the same location as your DB VM
b. Select Backup Items => SQL Database in Azure VM.
Click on the Add button
c. Select on the Configure Backup and select your DB form the options.
d. Check the progress in view details.
2. Set up Backup Policy
3. Assign the backup policy to the DB
4. Initiate the first Full Backup
a. Initiate the first full backup from the Azure Portal by selecting the Backup item from the Recovery service vault and then clicking on the Backup Now option.
b. Check on the backup progress from the Backup Jobs.

## ASR Steps
Note : ASR is already setup in current environment, Just Need to Perform Failover and Failback during DR activity. | Steps to follow During DR activity (Failover)
Login to Azure Portal .
To set up an Azure Site Recovery (ASR) for a Virtual Machine (VM) in Azure, follow these steps: | Verify the VM settings by going to the respective ASR recovery services vault, selecting the replicated VM, and ensuring it is protected and healthy.
Prerequisites | Next, run the failover by selecting a recovery point [Latest], shutting down the machine, and clicking OK to initiate. Monitor the progress and commit when the Progression Completed.
Reprotect the VM in the secondary region, verifying the replication direction and target settings.
1. Azure Subscription: Ensure you have an active Azure subscription. | To fail back to the primary region, ensure the VM is healthy and synchronized, then select a recovery point and initiate the failover.
2. Azure VM: Ensure you have a VM running in Azure that you want to configure ASR for. | Reprotect the VMs again, reviewing the target settings.
3. Resource Group: Create or identify an existing resource group. | Finally, clean up resources, nothing that Site Recovery will automatically clean up machines with managed disks, while those with unmanaged disks must be manually deleted.
4. Recovery Services Vault: Create or identify an existing Recovery Services vault.
Steps
Step 1: Create a Recovery Services Vault
1. Sign in to Azure Portal: Go to Azure Portal.
2. Create a Recovery Services Vault:
Navigate to All services > Recovery Services vaults.
Click on Add.
Fill in the necessary details: name, subscription, resource group, and location.
Click Review + create and then Create.
Step 2: Configure the Recovery Services Vault
1. Open the Recovery Services Vault:
Go to the Recovery Services vaults blade and select your newly created vault.
2. Set up Backup:
In the vault, go to Backup.
In the Where is your workload running? section, select Azure.
In the What do you want to backup? section, select Azure Virtual Machine.
Click Prepare Infrastructure.
Step 3: Enable Site Recovery for the VM
1. Navigate to VM:
Go to Virtual machines in the Azure Portal.
Select the VM you want to enable ASR for.
2. Backup:
In the VM menu, click on Backup.
Select the Recovery Services vault created earlier.
Create a new backup policy or select an existing one.
Click Enable backup.
Step 4: Configure Replication Settings
1. Navigate to Site Recovery:
Go to your Recovery Services vault.
Click on Site Recovery in the left-hand menu.
2. Prepare Infrastructure:
Click on Prepare infrastructure.
In the Protection goal section, choose Azure as the source and target.
Click OK.
3. Configure Source:
Select the source resource group and the VM you want to replicate.
Click OK.
4. Target Configuration:
Select the target region for replication.
Choose the target subscription and resource group.
Specify the target network.
Click OK.
5. Replication Settings:
Configure the replication policy settings as per your requirements.
Click OK.
Step 5: Enable Replication
1. Enable Replication:
Review the replication settings and click Enable Replication.
Step 6: Monitor the Replication
1. Monitoring:
Navigate to the Site Recovery Jobs section in the Recovery Services vault.
Monitor the initial replication progress.
Ensure that the replication is completed successfully.
Additional Considerations
Test Failover: Regularly perform test failovers to ensure that your disaster recovery setup works correctly.
Update Replication Settings: Periodically review and update your replication settings based on any changes in your VM or infrastructure.
By following these steps, you can set up Azure Site Recovery for your virtual machine in Azure, ensuring that your VM can be replicated and recovered in case of a disaster.

## Lessons_Unlocking of users
Security team did not respond to firefighter request issues on Friday
RFCPGR Users needs to remain unlocked in PRP, PWM, PGW
RFCPB1 Users needs to remain unlocked in PGW
RFCPGR Users needs to remain unlocked in PGW
RFCPRP Users needs to remain unlocked in PGW
RFCUSER Users needs to remain unlocked in PGW
DNS Services between SAN, EUN & DNS Server were an issue